## Slide 1
Prof. Dr. Samir AFIFI
International Relation - Projects Coordinator
Sakarya University - Türkiye
samirafifi@sakarya.edu.tr
Phone: +905317744935
How to Manage Project Grant Effectively
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
06th - 10th May 2024 - Sakarya University – Türkiye

## Slide 2
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
What is Project Management
It is the application of:
        Processes, Methods, Skills, Knowledge, Techniques and Experience to achieve “Specific project objectives
It should conduct according to project acceptance criteria within agreed parameters

## Slide 3
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
Main five 5 stages of project management
Submitting Phase
  1- Project Initiation.
  2- Project Planning.
After Approval
  3- Project Execution.
  4- Project Monitoring and control (Quality Control and assurance).
  5- Project Closure (Sustainability).

## Slide 4
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
Project Management start with submitting new proposal
Project Management at Submitting Phase
  1- Initiation.
  2- Planning.
What should We know to start?
Points to consider when writing a proposal

## Slide 5
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
  Fund the right opportunity for your proposal
  Shape your proposal based on action priorities and funding rules
  Cross-check budget
  Help with administrative documents
1- Initiation!

## Slide 6
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
Right Opportunity:
KEY ACTION 2: Central Project
Main Objectives For CBHE
It shall address the advancement and challenges of HEIs located in eligible third countries not associated to the Program

## Slide 7
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
Regions | Countries
Western Balkans (Region 1) | Albania, Bosnia and Herzegovina, Kosovo*, Montenegro
Neighbourhood East (Region 2) | Armenia, Azerbaijan, Georgia, Moldova, Ukraine*
South-Mediterranean countries (Region 3) | Algeria, Egypt, Israel*, Jordan, Lebanon, Libya, Morocco, Palestine*, Syria**, Tunisia
Asia (Region 5) | 5a Bangladesh, Bhutan, Cambodia, China, DPR Korea, India, Indonesia, Laos, Malaysia, Maldives, Mongolia, Myanmar, Nepal, Pakistan, Philippines, Sri Lanka, Thailand, Vietnam 5b High income countries: Brunei, Hong Kong, Japan, Republic of Korea, Macao, Singapore and Taiwan
Central Asia (Region 6) | Afghanistan, Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan, Uzbekistan
Middle East (Region 7) | 7a Iran, Iraq, Yemen 7b High income countries: Bahrain, Kuwait, Oman, Qatar, Saudi Arabia, United Arab Emirates
Pacific (Region 8) | 8a Cook Islands, Fiji, Kiribati, Marshall Islands, Micronesia, Nauru, Niue, Palau, Papua New Guinea, Samoa, Solomon Islands, Timor-Leste, Tonga, Tuvalu, Vanuatu 8b High income countries: Australia, New Zealand
Sub-Saharan Africa (Region 9 ) | Angola, Benin, Botswana, Burkina Faso, Burundi, Cameroon, Cabo Verde, Central African Republic, Chad, Comoros, Congo, Congo - Democratic Republic of the, Côte d’Ivoire, Djibouti, Equatorial Guinea, Eritrea, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guinea, Guinea-Bissau, Kenya, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritania, Mauritius, Mozambique, Namibia, Niger, Nigeria, Rwanda, Sao Tome and Principe, Senegal, Seychelles, Sierra Leone, Somalia, South Africa, South Sudan, Sudan, Tanzania, Togo, Uganda, Zambia, Zimbabwe
Latin America (Region 10) | Argentina, Bolivia, Brazil, Chile, Colombia, Costa Rica, Ecuador, El Salvador, Guatemala, Honduras, Mexico, Nicaragua, Panama, Paraguay, Peru, Uruguay and Venezuela
Caribbean (Region 11) | Antigua & Barbuda, Bahamas, Barbados, Belize, Cuba, Dominica, Dominican Republic, Grenada, Guyana, Haiti, Jamaica, St Kitts and Nevis, St Lucia, St Vincent & Grenadines, Suriname, Trinidad & Tobago

## Slide 8
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
Points to be considered to manage writing a new proposal
2- Planning!
Find a Project idea
Choose appropriate and committed partners
Needs analysis
Develop logical framework
Formulate WPs and tasks

## Slide 9
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
Points to be considered to manage writing a new proposal
2- Planning!
Ensure adequate human resources, time, and needed tools for project organization.
Committed management.
Make sure communication is planned and continuous

## Slide 10
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
At first you need a concrete project idea in line with the CBHE objectives;
  Define a Project Concept
Once the idea is defined, start locally in your institution consulting colleagues and departments with experience in international projects;
Find the right partners for establishing an international partnership based on trust and shared objectives;
  Project consortium (National, Regional project, multiregional )
    Project coordinator?
    Project Partners?
    Associated Partners?
As an applicant interested in CBHE, you should start with:
At the end of this phase, Project is submitted

## Slide 11
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
  3- Execution.
  4- Monitoring and control (Quality Control and Quality assurance).
  5- Closure (Sustainability)
Project Management After Project Approval Implementing Phase

## Slide 12
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
Getting start
Points to be considered
3- Execution
Organise kick-off meeting
  Review project plan and revise if necessary
  Take into account internal/external changes and limitations
  Allocate roles according to work packages
  Create project management structure (management board, other boards)
  Set up communication rules
  Revise budget allocation if necessary
Produce Partnership Agreement

## Slide 13
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
Keep partners
informed of the evaluation results and the remedial actions taken
4- Monitoring and control, QUALITY ASSURANCE
Activities Monitoring
Internal Quality Assurance
External Quality Assurance

## Slide 14
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
5- Closure (Sustainability)
Project results should be sustainable and should continue to be used /updated after end of project funding
Financial / administrative / legislative achievements
Continuation of developed programs
Continued cooperation with project partners
        Student and staff mobility
        Joint degrees
        Research cooperation
        New projects
Continued cooperation with
        stakeholders at national/ regional cross regional levels

## Slide 15
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
Ensuring Sustainability
Good Communication, Dissemination and Exploitation

## Slide 16
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University
Communication Dissemination and Exploitation

## Slide 17
INTERNATIONAL STAFF WEEK 2024
Global Bridges and Green Visions: Erasmus+ Sustainability Dialogues
International Relation - Sakarya University